## Product Backlog
2D Three-Player Soccer Game — Product Backlog
Kirkwood Community College — Software Design & Development — Team: Smeet Joshi (SJ), Tabir (TY), Eli (EK)
Total Tasks | 47 | Total Est. Hours | 158 | Completed Tasks | 47 | Completed Hours | 158
Priority key: 1 = Very Important 2 = Important 3 = Lower Priority
Task ID | Category | Task | Description | Est. Hours | Priority | Status | Completed By | Sprint
1 | Planning | Confirm project concept and game rules | Finalize the basic 2D soccer game concept, match rules and scope. | 2 | 1 | Completed | SJ, TY, EK | Week 1
2 | Planning | Define teams and player roles | Set two teams with 3 players each - 1 defender and 2 front players. | 2 | 1 | Completed | SJ, TY, EK | Week 1
3 | Analysis | Write requirements analysis | Document functional and non-functional requirements for the basic game. | 4 | 1 | Completed | SJ, TY, EK | Week 1
4 | Design | Design field, goal and UI layout | Plan the soccer field, goal areas, scoreboard area, timer and menu placement. | 4 | 1 | Completed | SJ, TY, EK | Week 1
5 | Design | Write use cases | Create use cases for starting the game, moving players, scoring, pausing and exiting. | 2 | 2 | Completed | SJ, TY, EK | Week 1
6 | Design | Create CRC cards | Define responsibilities and collaborators for core classes. | 2 | 2 | Completed | SJ, TY, EK | Week 1
7 | Design | Create UML class detail diagram | Draw a detailed UML class diagram for SoccerGame, Team, Player, Ball, GameTimer, GameMenu, Field. | 2 | 2 | Completed | SJ, TY, EK | Week 1
8 | Design | Create UML relationship diagram | Show class associations and connections between the main game classes. | 2 | 2 | Completed | SJ, TY, EK | Week 1
9 | Design | Create parent/child relationship diagram | Draw the parent/child relationship diagram for the game. | 2 | 2 | Completed | SJ, TY, EK | Week 1
10 | Scrum | Create initial product backlog | List all major tasks, estimates hours, rank, status and sprint completion column. | 2 | 1 | Completed | SJ, TY, EK | Week 1
11 | Scrum | Complete Week 1 scrum artifacts | Prepare Week 1 kanban board, work log, worksheet answers, and backlog update. | 2 | 2 | Completed | SJ, TY, EK | Week 1
12 | Design | Draft class responsibilities and game states | Define SoccerGame, Team, Player, Ball, GameTimer, GameMenu, and game states. | 3 | 1 | Completed | SJ, TY, EK | Week 1
13 | Design | Update UML diagrams after implementation changes | Revise UML class and relationship diagrams if the code design changes during development. | 2 | 2 | Completed | SJ | Week 2
14 | Setup | Set up project structure and game loop | Create project files, main class, game panel/window and main loop. | 6 | 1 | Completed | SJ | Week 2
15 | Coding | Start Field class and field boundaries | Create the field object and set playable area boundaries. | 3 | 1 | Completed | TY, EK | Week 2
16 | Coding | Start Team class | Store team name, team score and references to team players. | 2 | 2 | Completed | TY, EK | Week 2
17 | Coding | Start Player class | Create player properties, movement state, team, role and position handling. | 6 | 1 | Completed | TY, EK | Week 2
18 | Coding | Start Ball class | Create ball properties, movement logic and reset behavior. | 5 | 1 | Completed | TY, EK | Week 2
19 | UI | Draw field, goals, scoreboard and timer area | Render the main field and heads-up display on the screen. | 4 | 1 | Completed | SJ, EK | Week 2
20 | UI | Draw players and ball | Display both teams and the ball using shapes or sprites. | 3 | 1 | Completed | SJ | Week 2
21 | Gameplay | Set starting positions and reset positions | Place all players and the ball at correct starting locations. | 2 | 1 | Completed | SJ, EK | Week 2
22 | Gameplay | Add Team 1 movement controls | Map keys and movement behavior for Team 1 players. | 5 | 1 | Completed | TY | Week 2
23 | Gameplay | Add Team 2 movement controls | Map keys and movement behavior for Team 2 players. | 5 | 1 | Completed | TY | Week 2
24 | Gameplay | Restrict players within field boundaries | Prevent players from moving outside the field. | 2 | 1 | Completed | TY | Week 2
25 | Gameplay | Add ball-player collision logic | Let player contact move or kick the ball correctly. | 6 | 1 | Completed | TY, EK | Week 2
26 | Gameplay | Add ball-boundary collision logic | Handle ball contact with field edges and out-of-bounds behavior. | 3 | 1 | Completed | TY | Week 2
27 | Gameplay | Add goal detection | Detect when the ball fully enters either goal area. | 4 | 1 | Completed | TY, EK | Week 2
28 | Gameplay | Add score update logic | Increase the correct team score after a goal. | 2 | 1 | Completed | SJ | Week 2
29 | Gameplay | Add timer logic and display updates | Start, pause, reset and display the game timer. | 4 | 1 | Completed | SJ | Week 2
30 | Menu | Create New Game action | Reset the match, score, timer, players and ball. | 2 | 1 | Completed | SJ | Week 2
31 | Menu | Create Pause/Resume action | Pause gameplay and timer, then allow play to resume. | 2 | 1 | Completed | SJ | Week 2
32 | Menu | Create Exit Game action | Allow the user to close the game cleanly. | 1 | 2 | Completed | SJ | Week 2
33 | Gameplay | Implement game state manager | Handle menu, playing, paused and match end states. | 5 | 1 | Completed | SJ | Week 2
34 | Gameplay | Apply defender near-goal rule | Keep the defender role focused near the goal area. | 3 | 2 | Completed | SJ | Week 3
35 | Gameplay | Apply front-player positioning rule | Keep the two front players in attacking play areas. | 2 | 2 | Completed | SJ | Week 3
36 | Gameplay | Add kick/pass interaction | Allow players to send the ball forward intentionally. | 5 | 1 | Completed | EK | Week 3
37 | Gameplay | Add end of match condition | Stop the match when the timer reaches zero or the chosen condition is met. | 2 | 2 | Completed | SJ | Week 3
38 | Gameplay | Add restart after goal flow | Pause briefly after goals and reset to starting positions. | 2 | 1 | Completed | SJ | Week 3
39 | Testing | Test player movement | Check movement, controls and field restrictions. | 4 | 1 | Completed | TY | Week 3
40 | Testing | Test ball movement and collisions | Check ball movement, collisions and bounce/reset behavior. | 4 | 1 | Completed | EK | Week 3
41 | Testing | Test score, timer and menu actions | Verify score, timer, New Game, Pause and Exit work correctly. | 4 | 1 | Completed | TY | Week 3
42 | Debugging | Debug gameplay issues | Fix bugs found in movement, collision, scoring or state transitions. | 8 | 1 | Completed | SJ, TY, EK | Week 4
43 | Cleanup | Refactor code and add comments | Clean code structure and add useful comments for readability. | 5 | 2 | Completed | SJ, TY, EK | Week 4
44 | Testing | Integration testing and playtest | Run full match testing to confirm the basic game is playable. | 5 | 1 | Completed | SJ, TY, EK | Week 4
45 | Debugging | Fix bugs after playtest | Resolve remaining issues found during integration testing. | 6 | 1 | Completed | SJ, TY, EK | Week 4
46 | Release | Final basic playable build check | Verify the game is stable and ready for instructor demonstration. | 3 | 1 | Completed | SJ, TY, EK | Week 4
47 | Gameplay | Set player zone | Set each player's zone so that they get triggered as soon as the ball reaches the zone. | 2 | 2 | Completed | EK | Week 3

## Summary
Backlog Summary
Status | Task Count | Hours | Category | Hours
Completed | 47 | 158 | Analysis | 4
In Progress | 0 | 0 | Cleanup | 5
Not Started | 0 | 0 | Coding | 16
|  |  | Debugging | 14
|  |  | Design | 19
|  |  | Gameplay | 54
|  |  | Menu | 5
|  |  | Planning | 4
|  |  | Release | 3
|  |  | Scrum | 4
|  |  | Setup | 6
|  |  | Testing | 17
|  |  | UI | 7